## Slide 1: Project Charter: Hospital Management and Services Team: Mohammad Adil, Abhinaya Singampalli, Ishika Rajawat, Urvashi Bhurase Start Date: 01/17/2023 End Date: 04/25/23
Case for change / Problem Statement
During covid, many patients had faced difficulty in finding the near by hospitals and available beds to admit in the hospital. Many people are not aware of best practices to identify the symptoms of a particular disease. People find difficulties in finding the hospitals that accepts the medical insurance.
Objectives / Goal statements
To integrate all the hospitals list and their geographic location and the availability of beds. To include videos which help patients take minimal medication at home and get medicines prescribed by a AI assistant based on symptoms. To include the list of insurance companies that are accepted by all the hospitals.
In Scope | Out of Scope
Application development | Assist patients to navigate through the app
Gathering hospitals information | Insurance reimbursement
Record informatory videos | Providing physical assistance
Constraint Matrix |  |  | 
Priority (High to Low) | Scope(H) | Time(M) | Cost(L)
Top Risks (max. 5)
Not able to update real-time data of beds availability in the hospital AI not suggesting correct disease Insurance company list is not up to date Internal server crash while building the application Not able to load the collected data into the application
Deliverables & Milestones (High Level Milestone Plan) |  | 
Key Deliverable | Milestone Name (MS) | Planned MS Date
Project Charter | Project Charted Submission | 01/31/2023
Collect hospital data | Data ready to integrate | 02/20/2023
Application Development | Application Developed | 03/10/2023
Data integration to the application | Data Integration Done | 03/23/2023
Add application features | All features are added | 04/10/2023
Application Testing | Application tested | 04/18/2023
Product Release | Product released | 04/25/23

## Slide 2: Project Charter: Hospital Management and Services Team: Mohammad Adil, Abhinaya Singampalli, Ishika Rajawat, Urvashi Bhurase Start Date: 01/17/2023 End Date: 04/25/23
Business Plan
Our Vision is to provide people with dynamic healthcare information and derive greater satisfaction through the optimal healthcare facilities as per their choice. Our mission is to design and develop an integrated mobile application that helps customers to find nearby hospitals along with health insurance information provided that will help them take an informed decision and get optimal healthcare services. The success criteria are - When the customers can successfully navigate to the hospitals in their vicinity, accept their health insurance and get free or subsidized treatments thus saving their money. - It is saving their time by providing them with information about available beds in hospitals during a pandemic like COVID-19. - A large number of downloads and user registration made through the application. - Huge number of appointments made through the application in a day. There are a few competitors available in the market that are Health service providers like Pharm Easy which helps patients to order medicines, and health products, book health check-up packages at a few certified laboratories, and book appointments with doctors only. But our idea comes under Health service, but we have a few differentiators when compared to other competitors. The key USPs are - We are giving information on the availability of beds in each hospital. - We will be providing informative videos of self-medication. - We include the list of insurance companies accepted by each hospital and help the customer choose the hospital and claim the insurance.